## Reserve Price
Zee5
Week
Reserve Price - Dynamic Pricing
| Data Provisioning & understanding | Duration (Days) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Agreement on Data Understanding, creating Data Dictonaries | 1 | bar: 1
2 | Zee5 session/traffic data, cookie data repository | 2 | bar: 1 to 2
AdExchange & 3rd Party Data | bar: 1 to 2
3 | Building DataLake & DB pipleining | 2 | bar: 1 to 2
Data Cleaning & Analytical Dataset creation
4 | Activities designated - Pricing data sanity check - Outlier control/treatment - Reserve Price - Distribution plots | 10 | bar: 2
Pricing Elasticity
5 | - Reserve Price elasticity check for Success/Missed bid cases (Demand-Price curve analysis) | 10 | bar: 3
Dynamic Pricing Engine
Log-Normal Price Optimization (Optimal Auction Theory | bar: 4 to 5
6 | Game Tree based Heuristics | 15 | bar: 5 to 6
True Price Engine: - Scenario based planning for optimal Reserve price, with maximum conversion & Forecasted Traffic/Impressions | bar: 6
Measurement Using Pre-Post Analysis
| Test-Control Framework: - Identified Similar Ad profile based Bidding scenarios for Test and Control Groups - Measure Lift% based on the True Price Engine based Reserve Pricing |  | 7: Post Reserve Pricing Framework Implementation

## CTR Prediction
Zee5
Week
Click-Through-Rate Prediction
| Data Provisioning & understanding | Duration (Days) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Agreement on Data Understanding, creating Data Dictonaries | 1 | bar: 1
2 | Zee5 session/traffic data, cookie data repository | 2 | bar: 1
Ad Space/ Banner Tracking info: captured by Adobe Analytics/Google Analytics | bar: 1 to 2
3 | Event level (Click) Data & user characteristics extract retrieved via AA or GA | 2 | bar: 1 to 2
Data Cleaning & Analytical Dataset creation
4 | Activities designated - Standardization of vectors, Outlier treatment - Variable transformations - Derived Variable/Flag creations | 10 | bar: 3
Analytical Dataset Creation
User Profile System: - User Id mapping to retrieve characteristics like age, gender, and interest preferences Time Characteristics: - Behavioral aspects like varying interest captured during different period of the day based on pageviews Click event system: - Click events historical data, click to conversion metrics Ad Id Characteristics: - Ad title, Ad text, keywords etc. info | bar: 4
CTR Prediction Modeling
ML Frameworks
- Naive Bayes - Hierarchical Bayesian Model - AdaBoost - Support vector regression | bar: 5 to 6
Deep Learning Frameworks
- DeepFM - xDeepFM - FiBiNET - Fi-GNN - NormDNN - AutoInt | bar: 7 to 8

## AdSpace Inventory Management
Zee5
Week
AdSpace Inventory Management
| Data Provisioning & understanding | Duration (Days) | 1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Agreement on Data Understanding, creating Data Dictonaries | 1 | bar: 1
2 | Zee5 session/traffic data, cookie data repository | 2 | bar: 1
Ad Space/ Banner Tracking info: captured by Adobe Analytics/Google Analytics | bar: 1
3 | AdSpace : Historical Ad Suppliers and Campaign data | 2 | bar: 1
Data Cleaning & Analytical Dataset creation
4 | Activities designated - Standardization of vectors, Outlier treatment - Variable transformations - Derived Variable/Flag creations | 10 | bar: 2
Analytical Dataset Creation
User Profile System: - User Id mapping to retrieve characteristics like age, gender, and interest preferences Historical Surfing Session Cookies: - Top Categories / keyword searched /page views based behavioral data Ad Suppliers data: - Category wise Ad campaigns listing from probable list of Ad Suppliers | bar: 2 to 3
LSTM Based Multi-Class Classifier
- Based on all Historic Clicks-No Click event across all Ad categories, build Multi-class classification using LSTM to model user responsee & user interest | bar: 4 to 6
Model Ranking Framework
- Prediction Ranks based Banner Mapping - Validation by n-tile Ranks Classifcation | bar: 6
Ad Selection (Scenario based Implementation)
- Scenario 1: Based on Ranked Categories, respective Contract based Supplier ad gets displayed - Scenario 2: RTB implemented among the Ad Suppliers for each of the shortlisted categories | bar: 7